## Sheet1
S/N | Area | Finding | Corrective Action | Observation Date | Responsible Person | Category | Status | Date Closed | Responsible Company | Assignee Company | Observation Type
1 | GOSP- 06 | Supervisor not using mandatory PPE (Helmet & safety glasses) while supervising grinding work. | The supervisor was instructed to always wear the mandatory helmet and safety glasses in the work area. | 29/08/2026 | WPR/Foreman | PPE | Closed | 29/08/2026 | HEISCO | HEISCO | Major
2 | GOSP- 06 | Hot work (cutting/grinding) area was not barricaded or protected with a fire blanket. | Instructed the Fire Watcher to properly cover the activity with a fire blanket and barricade the area. | 29/08/2026 | Site Supervisor | Welding & Cutting Operation | Closed | 29/08/2026 | HEISCO | HEISCO | Major
3 | GOSP- 06 | Helper was standing on an unsecured small metal piece while a fitter was grinding it, placing his foot in the line of fire. | Instructed the Fitter and Helper to secure the workpiece with a proper tool (vise/clamp) and to avoid being in the line of fire. | 29/08/2026 | Electrician | Positions of People (Behavioral) | Closed | 29/08/2026 | HEISCO | HEISCO | Major
4 | GOSP - 05 | Protruding nails were not removed or bent from dismantled wooden boxes before disposal. | Workers were instructed to remove or bend all protruding nails from wood waste before disposal. | 29/08/2026 | Site Engineer | Sharp Edge Protection | Closed | 29/08/2026 | HEISCO | HEISCO | Minor
5 | GOSP - 05 | A portable water tank was found unattended at the workplace. | The unattended water tank was removed from the workplace. | 29/08/2026 | Mechanical Engineer | Housekeeping & Material Arrangement | Closed | 29/08/2026 | HEISCO | HEISCO | Minor
6 | GOSP - 05 | During chipping activity, the designated Fire Watcher was absent from his post. | The Fire Watcher was instructed to remain at the hot work location and continuously monitor the activity. | 29/08/2026 | Civil Engineer | Welding & Cutting Operation | Closed | 29/08/2026 | HEISCO | HEISCO | Major
7 | GOSP - 05 | Scaffold tag was found with an incorrect inspection date. | The scaffold tag was corrected with the proper date as per the two-week standard. | 29/08/2026 | Electrician | Scaffolding | Closed | 29/08/2026 | HEISCO | HEISCO | Minor
8 | GOSP - 05 | An air blower was being used for dust cleaning without any dust control measures (e.g., water suppression). | Effective dust control measures were implemented before work was allowed to resume. | 29/08/2026 | Civil Supervisor | Housekeeping & Material Arrangement | Closed | 29/08/2026 | HEISCO | HEISCO | Minor
9 | GOSP - 05 | Personnel were off-loading steel materials at night without wearing clear safety glasses. | All personnel were instructed to wear clear safety glasses for night work. | 29/08/2026 | Site Engineer | PPE | Closed | 29/08/2026 | HEISCO | HEISCO | Minor
10 | GOSP - 02 | Compactor operator was working at a high speed despite hot weather conditions, increasing heat stress risk. | The operator was coached on the dangers of heat stress and instructed to work at a safe pace according to conditions. | 29/08/2026 | Mechanical Engineer | Worksite Medical Facilities and Related Requirements | Closed | 29/08/2026 | HEISCO | HEISCO | Major
11 | GOSP - 02 | A compressor was in use without being properly grounded. | The compressor was immediately taken out of service until it was properly grounded. | 29/08/2026 | Civil Engineer | Electrical | Closed | 29/08/2026 | HEISCO | HEISCO | Major
12 | GOSP - 02 | A compressor was found with a missing pre-use inspection checklist. | The supervisor was instructed not to use the equipment until a proper pre-use inspection is completed and documented. | 29/08/2026 | Rigger 3 | Inspection | Closed | 29/08/2026 | HEISCO | HEISCO | Minor
13 | GOSP - 02 | SIF Modification activity was ongoing without the required supervision. | The job was stopped until the responsible supervisor was present at the worksite. | 29/08/2026 | Site Supervisor | Permit To Work | Closed | 29/08/2026 | HEISCO | HEISCO | Major
14 | GOSP - 02 | Personnel were working without an umbrella during an 'Orange Flag' (high heat) condition. | Work was stopped and umbrellas were provided to the workers as per heat stress plan requirements. | 29/08/2026 | Electrician | Worksite Medical Facilities and Related Requirements | Closed | 29/08/2026 | HEISCO | HEISCO | Major
15 | GOSP - 02 | Unauthorized personnel were observed standing under a suspended load during a lifting operation. | The lifting area was immediately cleared and re-barricaded to prevent unauthorized entry. | 29/08/2026 | Civil Supervisor | Positions of People (Behavioral) | Closed | 29/08/2026 | HEISCO | HEISCO | Major
16 | GOSP - 03 | Rigging softeners used for sharp edge protection on steel structures were not long enough to protect the web slings from damage. | The rigger was instructed to use softeners of the proper length that cover all sharp edges before lifting. | 30/08/2026 | Site Engineer | Cranes & Heavy Lifting | Closed | 30/08/2026 | HEISCO | HEISCO | Major
17 | GOSP - 03 | An electrical cable was routed on the ground where a steel assembly was in progress, creating a damage risk. | The electrical cable was relocated away from the work area to protect it from damage. | 30/08/2026 | Mechanical Engineer | Electrical | Closed | 30/08/2026 | HEISCO | HEISCO | Minor
18 | GOSP - 03 | Excavation was proceeding with a blunt pickaxe, which is an inefficient and unsafe tool for the task. | The blunt hand tool was replaced with a new, sharp pickaxe suitable for the work. | 30/08/2026 | Civil Engineer | Hand & Power Tools | Closed | 30/08/2026 | HEISCO | HEISCO | Minor
19 | GOSP - 03 | High Heat Stress Index (Category IV) was observed, but work continued. | The job was immediately stopped until the heat stress category returned to a safe level. | 30/08/2026 | WPR/Foreman | Worksite Medical Facilities and Related Requirements | Closed | 30/08/2026 | HEISCO | HEISCO | Major
20 | GOSP - 03 | Backfill material was unloaded less than 0.6 meters from the edge of an excavation. | The operator was instructed to always maintain a minimum distance of 0.6 meters from the excavation edge when placing spoil or materials. | 30/08/2026 | Site Supervisor | Trenching/Excavating & Shoring | Closed | 30/08/2026 | HEISCO | HEISCO | Major
21 | GOSP - 03 | The location mentioned on a cable locating sketch for a cutting permit was incorrect. | The permit was rescinded. The excavation point was re-scanned, and a new, correct sketch was made before work was re-authorized. | 30/08/2026 | Electrician | Permit To Work | Closed | 30/08/2026 | HEISCO | HEISCO | Major
22 | GOSP - 03 | No emergency eyewash station was available in the saltwater work area. | A portable, shaded eyewash station was installed in a clearly marked, accessible location. | 30/08/2026 | Civil Supervisor | Worksite Medical Facilities and Related Requirements | Closed | 30/08/2026 | HEISCO | HEISCO | Major
23 | LAYDOWN | Scaffolding material was stored at the edge of an excavation, creating a surcharge load. | All materials were removed from the edge of the excavation to a designated storage area. | 03/09/2026 | Scaffolding Supervisor | Scaffolding | Closed | 03/09/2026 | HEISCO | HEISCO | Major
24 | LAYDOWN | Wooden planks with protruding nails were found in the work area. | All wood with protruding nails was collected, and the nails were removed or bent over. | 03/09/2026 | Rigger 3 | Housekeeping & Material Arrangement | Closed | 03/09/2026 | HEISCO | HEISCO | Minor